## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Collect and review healthcare operational datasets | Must | None | Shambhavi | Completed
Sprint 1 | Sprint 1 | US-02 | Clean patient, admission, treatment, staff, bed and facility data | Must | US-01 | Harshada | Completed
Sprint 1 | Sprint 1 | US-03 | Handle missing values, duplicates and inconsistent data types | Must | US-02 | Harshada | Completed
Sprint 1 | Sprint 1 | US-04 | Create cleaned and standardized datasets for analysis | Must | US-02, US-03 | Shambhavi | Completed
Sprint 1 | Sprint 1 | US-05 | Integrate healthcare datasets for operational analysis | Must | US-04 | Harshada | Completed
Sprint 1 | Sprint 1 | US-06 | Define and validate operational KPI calculations | Must | US-05 | Khushi | Completed
Sprint 2 | Sprint 2 | US-07 | Analyze patient demographics and registration activity | Must | US-05 | Shambhavi | Completed
Sprint 2 | Sprint 2 | US-08 | Analyze admissions, discharges and patient flow | Must | US-05, US-06 | Harshada | Completed
Sprint 2 | Sprint 2 | US-09 | Analyze treatment demand and treatment status | Must | US-05, US-06 | Khushi | Completed
Sprint 2 | Sprint 2 | US-10 | Analyze department workload and demand concentration | Should | US-08, US-09 | Khushi | Completed
Sprint 2 | Sprint 2 | US-11 | Build patient-flow and service-demand dashboard views | Must | US-08, US-09 | Harshada | Completed
Sprint 3 | Sprint 3 | US-12 | Calculate bed occupancy and available-bed metrics | Must | US-05, US-06 | Khushi | Completed
Sprint 3 | Sprint 3 | US-13 | Analyze maintenance beds and capacity reconciliation | Must | US-12 | Harshada | Completed
Sprint 3 | Sprint 3 | US-14 | Analyze workforce distribution and shift utilization | Must | US-05 | Khushi | Completed
Sprint 3 | Sprint 3 | US-15 | Calculate staff efficiency and fulfillment rate | Must | US-14 | Khushi | Completed
Sprint 3 | Sprint 3 | US-16 | Build facilities, beds and workforce dashboard views | Must | US-12, US-15 | Harshada | Completed
Sprint 4 | Sprint 4 | US-17 | Analyze patient, admission and facility activity by city | Must | US-05 | Shambhavi | Completed
Sprint 4 | Sprint 4 | US-18 | Build geographic performance analysis and filters | Must | US-17 | Harshada | Completed
Sprint 4 | Sprint 4 | US-19 | Integrate operational KPIs into the executive dashboard | Must | US-06, US-11, US-16, US-18 | Harshada | Completed
Sprint 4 | Sprint 4 | US-20 | Validate KPIs, filters, calculations and data consistency | Must | US-19 | Khushi | Completed
Sprint 4 | Sprint 4 | US-21 | Test no-data scenarios, chart refresh and dashboard navigation | Must | US-19 | Harshada | Completed
Sprint 4 | Sprint 4 | US-22 | Document findings, recommendations and final project outcome | Should | US-20, US-21 | All Members | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTE: Task sizing is 0.5–12 hours. Day columns represent sprint-relative planned effort; exact calendar dates were not supplied.
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 228 | 17 | 19 | 19 | 17 | 19 | 19 | 14 | 16 | 14 | 14 | 16 | 14 | 14 | 16
SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
US-01 | T-01 | Identify required healthcare datasets |  |  | Shambhavi | Data Collection | Completed | 3 | Day 1: 3
US-01 | T-02 | Review dataset sources and fields |  |  | Shambhavi | Data Analysis | Completed | 5 | Day 2: 5
US-01 | T-03 | Confirm datasets are ready for processing |  |  | Shambhavi | Validation | Completed | 3 | Day 3: 3
US-02 | T-04 | Load healthcare datasets into the processing workflow |  |  | Shambhavi | Data Processing | Completed | 3 | Day 4: 3
US-02 | T-05 | Clean patient, admission, treatment, staff, bed and facility data |  |  | Shambhavi | Data Cleaning | Completed | 5 | Day 5: 5
US-02 | T-06 | Validate cleaned records and field consistency |  |  | Shambhavi | Validation | Completed | 3 | Day 6: 3
US-03 | T-07 | Profile missing values, duplicates and data types |  |  | Shambhavi | Data Quality | Completed | 3 | Day 7: 3
US-03 | T-08 | Apply missing-value and duplicate handling rules |  |  | Shambhavi | Data Cleaning | Completed | 5 | Day 8: 5
US-03 | T-09 | Validate data quality after cleaning |  |  | Shambhavi | Validation | Completed | 3 | Day 9: 3
US-04 | T-10 | Standardize column names and categorical values |  |  | Shambhavi | Data Cleaning | Completed | 3 | Day 10: 3
US-04 | T-11 | Standardize dates and numeric fields |  |  | Shambhavi | Data Transformation | Completed | 5 | Day 11: 5
US-04 | T-12 | Export and review cleaned datasets |  |  | Shambhavi | Data Processing | Completed | 3 | Day 12: 3
US-05 | T-13 | Map common keys across healthcare datasets |  |  | Shambhavi | Data Integration | Completed | 3 | Day 13: 3
US-05 | T-14 | Create integrated analytical datasets |  |  | Shambhavi | Data Integration | Completed | 5 | Day 14: 5
US-05 | T-15 | Validate relationships and record consistency |  |  | Shambhavi | Validation | Completed | 3 | Day 1: 3
US-06 | T-16 | Define KPI formulas and business meaning |  |  | Khushi | KPI Definition | Completed | 3 | Day 2: 3
US-06 | T-17 | Implement KPI calculations for operational analysis |  |  | Khushi | KPI Development | Completed | 5 | Day 3: 5
US-06 | T-18 | Cross-check KPI results against source data |  |  | Khushi | Validation | Completed | 3 | Day 4: 3
SPRINT 2 BACKLOG
US-07 | T-19 | Prepare patient demographic analysis fields |  |  | Shambhavi | Data Analysis | Completed | 3 | Day 5: 3
US-07 | T-20 | Analyze age, gender, city and registration activity |  |  | Shambhavi | Analysis | Completed | 5 | Day 6: 5
US-07 | T-21 | Validate patient analysis outputs |  |  | Shambhavi | Validation | Completed | 3 | Day 7: 3
US-08 | T-22 | Prepare admission and discharge measures |  |  | Harsada | Analysis | Completed | 3 | Day 8: 3
US-08 | T-23 | Analyze admission trends and length of stay |  |  | Harsada | Analysis | Completed | 5 | Day 9: 5
US-08 | T-24 | Validate patient-flow calculations |  |  | Harsada | Validation | Completed | 3 | Day 10: 3
US-09 | T-25 | Prepare treatment type and status measures |  |  | Khushi | Analysis | Completed | 3 | Day 11: 3
US-09 | T-26 | Analyze treatment demand and completion |  |  | Khushi | Analysis | Completed | 5 | Day 12: 5
US-09 | T-27 | Validate treatment KPIs |  |  | Khushi | Validation | Completed | 3 | Day 13: 3
US-10 | T-28 | Calculate department workload measures |  |  | Khushi | Analysis | Completed | 3 | Day 14: 3
US-10 | T-29 | Compare departmental demand and workload |  |  | Khushi | Analysis | Completed | 5 | Day 1: 5
US-10 | T-30 | Validate workload outputs |  |  | Khushi | Validation | Completed | 3 | Day 2: 3
US-11 | T-31 | Design patient-flow dashboard visuals |  |  | Harsada | Power BI | Completed | 3 | Day 3: 3
US-11 | T-32 | Build admission, discharge and treatment views |  |  | Harsada | Power BI | Completed | 5 | Day 4: 5
US-11 | T-33 | Test filters and visual interactions |  |  | Harsada | Validation | Completed | 3 | Day 5: 3
SPRINT 3 BACKLOG
US-12 | T-34 | Prepare bed status and capacity fields |  |  | Khushi | Analysis | Completed | 3 | Day 6: 3
US-12 | T-35 | Calculate occupancy and available-bed metrics |  |  | Khushi | DAX/KPI | Completed | 5 | Day 7: 5
US-12 | T-36 | Reconcile capacity calculations |  |  | Khushi | Validation | Completed | 3 | Day 8: 3
US-13 | T-37 | Identify maintenance-bed records |  |  | Khushi | Analysis | Completed | 3 | Day 9: 3
US-13 | T-38 | Calculate capacity reconciliation gap |  |  | Khushi | DAX/KPI | Completed | 5 | Day 10: 5
US-13 | T-39 | Validate capacity and maintenance measures |  |  | Khushi | Validation | Completed | 3 | Day 11: 3
US-14 | T-40 | Prepare staff and shift measures |  |  | Khushi | Analysis | Completed | 3 | Day 12: 3
US-14 | T-41 | Analyze staff by department and role |  |  | Khushi | Analysis | Completed | 5 | Day 13: 5
US-14 | T-42 | Validate assigned versus worked shifts |  |  | Khushi | Validation | Completed | 3 | Day 14: 3
US-15 | T-43 | Calculate staff efficiency and fulfillment measures |  |  | Khushi | DAX/KPI | Completed | 3 | Day 1: 3
US-15 | T-44 | Compare workforce utilization across departments |  |  | Khushi | Analysis | Completed | 5 | Day 2: 5
US-15 | T-45 | Validate workforce KPIs |  |  | Khushi | Validation | Completed | 3 | Day 3: 3
US-16 | T-46 | Design facilities and workforce visuals |  |  | Harsada | Power BI | Completed | 3 | Day 4: 3
US-16 | T-47 | Build bed, capacity and workforce pages |  |  | Harsada | Power BI | Completed | 5 | Day 5: 5
US-16 | T-48 | Test page filters and interactions |  |  | Harsada | Validation | Completed | 3 | Day 6: 3
SPRINT 4 BACKLOG
US-17 | T-49 | Prepare city-level patient and facility fields |  |  | Shambhavi | Data Analysis | Completed | 3 | Day 7: 3
US-17 | T-50 | Analyze patients, admissions and capacity by city |  |  | Shambhavi | Analysis | Completed | 5 | Day 8: 5
US-17 | T-51 | Validate geographic aggregations |  |  | Shambhavi | Validation | Completed | 3 | Day 9: 3
US-18 | T-52 | Configure geographic visual and location fields |  |  | Harsada | Power BI | Completed | 3 | Day 10: 3
US-18 | T-53 | Add city, department and date filters |  |  | Harsada | Power BI | Completed | 5 | Day 11: 5
US-18 | T-54 | Test geographic filtering and location display |  |  | Harsada | Validation | Completed | 3 | Day 12: 3
US-19 | T-55 | Select final executive KPIs and visuals |  |  | Harsada | Power BI | Completed | 3 | Day 13: 3
US-19 | T-56 | Assemble executive dashboard and navigation |  |  | Harsada | Power BI | Completed | 5 | Day 14: 5
US-19 | T-57 | Review dashboard consistency and usability |  |  | Harsada | Validation | Completed | 3 | Day 1: 3
US-20 | T-58 | Prepare KPI validation checklist |  |  | Khushi | Testing | Completed | 3 | Day 2: 3
US-20 | T-59 | Compare dashboard calculations with source/expected values |  |  | Khushi | Testing | Completed | 5 | Day 3: 5
US-20 | T-60 | Record and resolve calculation differences |  |  | Khushi | Defect Fixing | Completed | 3 | Day 4: 3
US-21 | T-61 | Test dashboard filter and chart refresh behavior |  |  | Harsada | Testing | Completed | 3 | Day 5: 3
US-21 | T-62 | Test no-data handling and navigation |  |  | Harsada | Testing | Completed | 5 | Day 6: 5
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Source datasets and ownership needed confirmation. | Confirmed six healthcare datasets, ownership and processing workflow.
Sprint 1 | Day 2 | Missing values, duplicates and inconsistent formats identified. | Applied cleaning and standardization rules in the data-processing workflow.
Sprint 2 | Day 1 | Patient-flow and treatment KPIs required validation. | Cross-checked KPI definitions and aggregation logic before dashboard development.
Sprint 2 | Day 3 | Department/date filters produced calculation differences. | Reviewed filter context and corrected affected calculations.
Sprint 3 | Day 2 | Bed capacity and occupancy measures needed reconciliation. | Validated total, occupied, available and maintenance-bed calculations.
Sprint 4 | Day 2 | Some geographic records were not displayed on the map. | Cleaned and standardized location values and revalidated geographic visuals.
Sprint 4 | Day 4 | Final dashboard refresh/deployment checks exposed issues. | Fixed filter/refresh, empty-data, layout and deployment issues; completed integration testing.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 |  |  | Harsada | Start validating visuals and filter interactions earlier | Stop leaving integration checks until the end | Continue Power BI development and dashboard review | Added repeated visual/filter validation during dashboard development.
1 | Sprint 1 |  |  | Khushi | Start documenting KPI assumptions alongside calculations | Stop correcting calculations only after visual discrepancies appear | Continue validating operational measures | Added KPI cross-checks and reconciled bed/workforce calculations.
1 | Sprint 1 |  |  | Shambhavi | Start recording data-quality issues as they are found | Stop relying on manual inspection for repeated cleaning tasks | Continue structured data preparation and quality checks | Strengthened preprocessing, standardization and geographic data checks.
4 | Sprint 2 |  |  | Harsada | Start validating visuals and filter interactions earlier | Stop leaving integration checks until the end | Continue Power BI development and dashboard review | Added repeated visual/filter validation during dashboard development.
4 | Sprint 2 |  |  | Khushi | Start documenting KPI assumptions alongside calculations | Stop correcting calculations only after visual discrepancies appear | Continue validating operational measures | Added KPI cross-checks and reconciled bed/workforce calculations.
4 | Sprint 2 |  |  | Shambhavi | Start recording data-quality issues as they are found | Stop relying on manual inspection for repeated cleaning tasks | Continue structured data preparation and quality checks | Strengthened preprocessing, standardization and geographic data checks.
7 | Sprint 3 |  |  | Harsada | Start validating visuals and filter interactions earlier | Stop leaving integration checks until the end | Continue Power BI development and dashboard review | Added repeated visual/filter validation during dashboard development.
7 | Sprint 3 |  |  | Khushi | Start documenting KPI assumptions alongside calculations | Stop correcting calculations only after visual discrepancies appear | Continue validating operational measures | Added KPI cross-checks and reconciled bed/workforce calculations.
7 | Sprint 3 |  |  | Shambhavi | Start recording data-quality issues as they are found | Stop relying on manual inspection for repeated cleaning tasks | Continue structured data preparation and quality checks | Strengthened preprocessing, standardization and geographic data checks.
10 | Sprint 4 |  |  | Harsada | Start validating visuals and filter interactions earlier | Stop leaving integration checks until the end | Continue Power BI development and dashboard review | Added repeated visual/filter validation during dashboard development.
10 | Sprint 4 |  |  | Khushi | Start documenting KPI assumptions alongside calculations | Stop correcting calculations only after visual discrepancies appear | Continue validating operational measures | Added KPI cross-checks and reconciled bed/workforce calculations.
10 | Sprint 4 |  |  | Shambhavi | Start recording data-quality issues as they are found | Stop relying on manual inspection for repeated cleaning tasks | Continue structured data preparation and quality checks | Strengthened preprocessing, standardization and geographic data checks.